## Sheet1
A basic exponential formula for calculating a range of dates for completion of User Stories

	Story Points	Weeks_Remaining	NTCF	BDC	MinWeeks	MaxWeeks	RangeWeeks	Earliest Date	Latest Date
	135	15	0.85	2.64	12.36	21.61	9.25	Fri 15 May 09	Sun 19 Jul 09

		Weeks from Story Points / The relationship between weeks and story points is non-linear / Story Points / Weeks
Points_per_Iteration	27.0000
Weeks_per_Iteration	3.0000

Reference_Week	12.0000
Exponential_Knee_Week	52.0000
Base_Exponential	2.7183
Max_Date_Multiplier	2.5000
Min_Date_Multiplier	1.0000

Story_Points	500.0000
Date_Today	Wed 18 Feb 09

Weeks_Remaining_Base_Reference	55.5556

Near_Time_Correction_Factor	0.9998
Base_Delta_Correction	7.9090

Min_Weeks_to_Completion	47.6466
Max_Weeks_to_Completion	75.3279

Min_Completion_Date	Sun 17 Jan 10
Max_Completion_Date	Fri 30 Jul 10

© Jamie Allsop 2006-2009
	Story Points	Weeks_Remaining	NTCF	BDC	MinWeeks	MaxWeeks	RangeWeeks	Min_Date	Max_Date

	1	0.11	0.01	0.01	0.1	0.13	0.03	Wed 18 Feb 09	Wed 18 Feb 09
	5	0.56	0.05	0.05	0.51	0.68	0.17	Sat 21 Feb 09	Sun 22 Feb 09
	10	1.11	0.09	0.1	1.01	1.37	0.36	Wed 25 Feb 09	Fri 27 Feb 09
	15	1.67	0.14	0.16	1.5	2.08	0.57	Sat 28 Feb 09	Wed 4 Mar 09
	20	2.22	0.18	0.23	1.99	2.8	0.8	Tue 3 Mar 09	Mon 9 Mar 09
	25	2.78	0.23	0.3	2.48	3.53	1.05	Sat 7 Mar 09	Sat 14 Mar 09
	30	3.33	0.27	0.38	2.95	4.28	1.33	Tue 10 Mar 09	Fri 20 Mar 09
	35	3.89	0.31	0.46	3.43	5.04	1.62	Sat 14 Mar 09	Wed 25 Mar 09
	40	4.44	0.35	0.55	3.89	5.82	1.93	Tue 17 Mar 09	Mon 30 Mar 09
	45	5	0.39	0.64	4.36	6.61	2.25	Fri 20 Mar 09	Sun 5 Apr 09
	50	5.56	0.43	0.74	4.81	7.41	2.6	Mon 23 Mar 09	Fri 10 Apr 09
	55	6.11	0.47	0.84	5.27	8.22	2.95	Thu 26 Mar 09	Thu 16 Apr 09
	60	6.67	0.5	0.95	5.72	9.04	3.33	Mon 30 Mar 09	Wed 22 Apr 09
	65	7.22	0.54	1.06	6.16	9.87	3.71	Thu 2 Apr 09	Tue 28 Apr 09
	70	7.78	0.57	1.17	6.61	10.71	4.1	Sun 5 Apr 09	Mon 4 May 09
	75	8.33	0.6	1.29	7.05	11.55	4.5	Wed 8 Apr 09	Sat 9 May 09
	80	8.89	0.63	1.4	7.49	12.39	4.91	Sat 11 Apr 09	Fri 15 May 09
	85	9.44	0.66	1.52	7.93	13.24	5.32	Tue 14 Apr 09	Thu 21 May 09
	90	10	0.68	1.64	8.36	14.09	5.73	Fri 17 Apr 09	Wed 27 May 09
	95	10.56	0.71	1.75	8.8	14.94	6.14	Mon 20 Apr 09	Tue 2 Jun 09
	100	11.11	0.73	1.87	9.24	15.79	6.54	Thu 23 Apr 09	Mon 8 Jun 09
	105	11.67	0.75	1.99	9.68	16.63	6.95	Sun 26 Apr 09	Sun 14 Jun 09
	110	12.22	0.77	2.1	10.12	17.47	7.35	Wed 29 Apr 09	Sat 20 Jun 09
	115	12.78	0.79	2.21	10.56	18.31	7.75	Sun 3 May 09	Fri 26 Jun 09
	120	13.33	0.8	2.32	11.01	19.14	8.13	Wed 6 May 09	Thu 2 Jul 09
	125	13.89	0.82	2.43	11.46	19.97	8.52	Sat 9 May 09	Tue 7 Jul 09
	130	14.44	0.83	2.54	11.9	20.79	8.89	Tue 12 May 09	Mon 13 Jul 09
	135	15	0.85	2.64	12.36	21.61	9.25	Fri 15 May 09	Sun 19 Jul 09
	140	15.56	0.86	2.75	12.81	22.42	9.61	Mon 18 May 09	Fri 24 Jul 09
	145	16.11	0.87	2.84	13.27	23.22	9.96	Thu 21 May 09	Thu 30 Jul 09
	150	16.67	0.88	2.94	13.73	24.02	10.3	Mon 25 May 09	Wed 5 Aug 09
	155	17.22	0.89	3.04	14.19	24.81	10.62	Thu 28 May 09	Mon 10 Aug 09
	160	17.78	0.9	3.13	14.65	25.6	10.95	Sun 31 May 09	Sun 16 Aug 09
	165	18.33	0.91	3.22	15.12	26.37	11.26	Wed 3 Jun 09	Fri 21 Aug 09
	170	18.89	0.92	3.3	15.59	27.15	11.56	Sun 7 Jun 09	Thu 27 Aug 09
	175	19.44	0.92	3.39	16.06	27.91	11.86	Wed 10 Jun 09	Tue 1 Sep 09
	180	20	0.93	3.47	16.53	28.68	12.15	Sat 13 Jun 09	Sun 6 Sep 09
	185	20.56	0.94	3.55	17	29.43	12.43	Wed 17 Jun 09	Sat 12 Sep 09
	190	21.11	0.94	3.63	17.48	30.18	12.7	Sat 20 Jun 09	Thu 17 Sep 09
	195	21.67	0.95	3.71	17.96	30.93	12.97	Tue 23 Jun 09	Tue 22 Sep 09
	200	22.22	0.95	3.78	18.44	31.67	13.23	Sat 27 Jun 09	Sun 27 Sep 09
	205	22.78	0.96	3.85	18.92	32.41	13.49	Tue 30 Jun 09	Fri 2 Oct 09
	210	23.33	0.96	3.93	19.41	33.15	13.74	Fri 3 Jul 09	Thu 8 Oct 09
	215	23.89	0.96	4	19.89	33.88	13.99	Tue 7 Jul 09	Tue 13 Oct 09
	220	24.44	0.97	4.07	20.38	34.61	14.23	Fri 10 Jul 09	Sun 18 Oct 09
	225	25	0.97	4.13	20.87	35.33	14.47	Tue 14 Jul 09	Fri 23 Oct 09
	230	25.56	0.97	4.2	21.35	36.06	14.7	Fri 17 Jul 09	Wed 28 Oct 09
	235	26.11	0.97	4.27	21.84	36.78	14.93	Mon 20 Jul 09	Mon 2 Nov 09
	240	26.67	0.98	4.33	22.33	37.5	15.16	Fri 24 Jul 09	Sat 7 Nov 09
	245	27.22	0.98	4.4	22.83	38.21	15.39	Mon 27 Jul 09	Thu 12 Nov 09
	250	27.78	0.98	4.46	23.32	38.93	15.61	Fri 31 Jul 09	Tue 17 Nov 09
	255	28.33	0.98	4.52	23.81	39.64	15.83	Mon 3 Aug 09	Sun 22 Nov 09
	260	28.89	0.98	4.59	24.3	40.36	16.05	Fri 7 Aug 09	Fri 27 Nov 09
	265	29.44	0.99	4.65	24.79	41.07	16.27	Mon 10 Aug 09	Wed 2 Dec 09
	270	30	0.99	4.71	25.29	41.78	16.49	Fri 14 Aug 09	Mon 7 Dec 09
	275	30.56	0.99	4.77	25.78	42.49	16.71	Mon 17 Aug 09	Sat 12 Dec 09
	280	31.11	0.99	4.84	26.28	43.2	16.92	Thu 20 Aug 09	Thu 17 Dec 09
	285	31.67	0.99	4.9	26.77	43.91	17.14	Mon 24 Aug 09	Tue 22 Dec 09
	290	32.22	0.99	4.96	27.26	44.62	17.35	Thu 27 Aug 09	Sun 27 Dec 09
	295	32.78	0.99	5.02	27.76	45.33	17.57	Mon 31 Aug 09	Fri 1 Jan 10
	300	33.33	0.99	5.08	28.25	46.04	17.78	Thu 3 Sep 09	Wed 6 Jan 10
	305	33.89	0.99	5.14	28.75	46.75	18	Mon 7 Sep 09	Mon 11 Jan 10
	310	34.44	0.99	5.2	29.24	47.46	18.22	Thu 10 Sep 09	Sat 16 Jan 10
	315	35	0.99	5.27	29.73	48.17	18.43	Mon 14 Sep 09	Thu 21 Jan 10
	320	35.56	0.99	5.33	30.23	48.88	18.65	Thu 17 Sep 09	Tue 26 Jan 10
	325	36.11	1	5.39	30.72	49.59	18.87	Mon 21 Sep 09	Sun 31 Jan 10
	330	36.67	1	5.45	31.21	50.3	19.09	Thu 24 Sep 09	Fri 5 Feb 10
	335	37.22	1	5.52	31.71	51.01	19.31	Sun 27 Sep 09	Wed 10 Feb 10
	340	37.78	1	5.58	32.2	51.73	19.53	Thu 1 Oct 09	Mon 15 Feb 10
	345	38.33	1	5.64	32.69	52.44	19.75	Sun 4 Oct 09	Sat 20 Feb 10
	350	38.89	1	5.71	33.18	53.16	19.98	Thu 8 Oct 09	Thu 25 Feb 10
	355	39.44	1	5.77	33.67	53.87	20.2	Sun 11 Oct 09	Tue 2 Mar 10
	360	40	1	5.84	34.16	54.59	20.43	Thu 15 Oct 09	Sun 7 Mar 10
	365	40.56	1	5.9	34.65	55.31	20.66	Sun 18 Oct 09	Fri 12 Mar 10
	370	41.11	1	5.97	35.14	56.03	20.89	Thu 22 Oct 09	Wed 17 Mar 10
	375	41.67	1	6.03	35.63	56.75	21.12	Sun 25 Oct 09	Mon 22 Mar 10
	380	42.22	1	6.1	36.12	57.47	21.35	Wed 28 Oct 09	Sat 27 Mar 10
	385	42.78	1	6.17	36.61	58.2	21.59	Sun 1 Nov 09	Thu 1 Apr 10
	390	43.33	1	6.24	37.1	58.92	21.83	Wed 4 Nov 09	Tue 6 Apr 10
	395	43.89	1	6.31	37.58	59.65	22.07	Sun 8 Nov 09	Sun 11 Apr 10
	400	44.44	1	6.37	38.07	60.38	22.31	Wed 11 Nov 09	Fri 16 Apr 10
	405	45	1	6.44	38.56	61.11	22.55	Sat 14 Nov 09	Wed 21 Apr 10
	410	45.56	1	6.51	39.04	61.84	22.8	Wed 18 Nov 09	Mon 26 Apr 10
	415	46.11	1	6.59	39.53	62.58	23.05	Sat 21 Nov 09	Sun 2 May 10
	420	46.67	1	6.66	40.01	63.31	23.3	Wed 25 Nov 09	Fri 7 May 10
	425	47.22	1	6.73	40.49	64.05	23.56	Sat 28 Nov 09	Wed 12 May 10
	430	47.78	1	6.8	40.97	64.79	23.81	Tue 1 Dec 09	Mon 17 May 10
	435	48.33	1	6.88	41.46	65.53	24.07	Sat 5 Dec 09	Sat 22 May 10
	440	48.89	1	6.95	41.94	66.27	24.33	Tue 8 Dec 09	Thu 27 May 10
	445	49.44	1	7.03	42.42	67.01	24.6	Fri 11 Dec 09	Wed 2 Jun 10
	450	50	1	7.1	42.9	67.76	24.86	Tue 15 Dec 09	Mon 7 Jun 10
	455	50.56	1	7.18	43.38	68.51	25.13	Fri 18 Dec 09	Sat 12 Jun 10
	460	51.11	1	7.26	43.85	69.26	25.4	Tue 22 Dec 09	Thu 17 Jun 10
	465	51.67	1	7.34	44.33	70.01	25.68	Fri 25 Dec 09	Wed 23 Jun 10
	470	52.22	1	7.42	44.81	70.76	25.96	Mon 28 Dec 09	Mon 28 Jun 10
	475	52.78	1	7.5	45.28	71.52	26.24	Fri 1 Jan 10	Sat 3 Jul 10
	480	53.33	1	7.58	45.76	72.28	26.52	Mon 4 Jan 10	Thu 8 Jul 10
	485	53.89	1	7.66	46.23	73.04	26.8	Thu 7 Jan 10	Wed 14 Jul 10
	490	54.44	1	7.74	46.7	73.8	27.09	Sun 10 Jan 10	Mon 19 Jul 10
	495	55	1	7.82	47.18	74.56	27.39	Thu 14 Jan 10	Sat 24 Jul 10
	500	55.56	1	7.91	47.65	75.33	27.68	Sun 17 Jan 10	Fri 30 Jul 10
	505	56.11	1	7.99	48.12	76.1	27.98	Wed 20 Jan 10	Wed 4 Aug 10
	510	56.67	1	8.08	48.59	76.87	28.28	Sun 24 Jan 10	Tue 10 Aug 10
	515	57.22	1	8.17	49.05	77.64	28.59	Wed 27 Jan 10	Sun 15 Aug 10
	520	57.78	1	8.26	49.52	78.42	28.89	Sat 30 Jan 10	Fri 20 Aug 10
	525	58.33	1	8.34	49.99	79.19	29.2	Tue 2 Feb 10	Thu 26 Aug 10
	530	58.89	1	8.43	50.45	79.97	29.52	Sat 6 Feb 10	Tue 31 Aug 10
	535	59.44	1	8.52	50.92	80.76	29.84	Tue 9 Feb 10	Mon 6 Sep 10
	540	60	1	8.62	51.38	81.54	30.16	Fri 12 Feb 10	Sat 11 Sep 10
	545	60.56	1	8.71	51.85	82.33	30.48	Mon 15 Feb 10	Fri 17 Sep 10
	550	61.11	1	8.8	52.31	83.12	30.81	Fri 19 Feb 10	Wed 22 Sep 10
	555	61.67	1	8.9	52.77	83.91	31.14	Mon 22 Feb 10	Tue 28 Sep 10
	560	62.22	1	8.99	53.23	84.7	31.48	Thu 25 Feb 10	Sun 3 Oct 10
	565	62.78	1	9.09	53.69	85.5	31.81	Sun 28 Feb 10	Sat 9 Oct 10
	570	63.33	1	9.19	54.15	86.3	32.16	Thu 4 Mar 10	Fri 15 Oct 10
	575	63.89	1	9.29	54.6	87.1	32.5	Sun 7 Mar 10	Wed 20 Oct 10
	580	64.44	1	9.39	55.06	87.91	32.85	Wed 10 Mar 10	Tue 26 Oct 10
	585	65	1	9.49	55.51	88.72	33.2	Sat 13 Mar 10	Mon 1 Nov 10
	590	65.56	1	9.59	55.97	89.53	33.56	Tue 16 Mar 10	Sat 6 Nov 10
	595	66.11	1	9.69	56.42	90.34	33.92	Fri 19 Mar 10	Fri 12 Nov 10
	600	66.67	1	9.8	56.87	91.16	34.29	Tue 23 Mar 10	Thu 18 Nov 10
	605	67.22	1	9.9	57.32	91.98	34.66	Fri 26 Mar 10	Tue 23 Nov 10
	610	67.78	1	10.01	57.77	92.8	35.03	Mon 29 Mar 10	Mon 29 Nov 10
	615	68.33	1	10.12	58.22	93.62	35.4	Thu 1 Apr 10	Sun 5 Dec 10
	620	68.89	1	10.22	58.66	94.45	35.78	Sun 4 Apr 10	Sat 11 Dec 10
	625	69.44	1	10.33	59.11	95.28	36.17	Wed 7 Apr 10	Fri 17 Dec 10
	630	70	1	10.44	59.56	96.11	36.56	Sat 10 Apr 10	Wed 22 Dec 10
	635	70.56	1	10.56	60	96.95	36.95	Wed 14 Apr 10	Tue 28 Dec 10
	640	71.11	1	10.67	60.44	97.79	37.35	Sat 17 Apr 10	Mon 3 Jan 11
	645	71.67	1	10.79	60.88	98.63	37.75	Tue 20 Apr 10	Sun 9 Jan 11
	650	72.22	1	10.9	61.32	99.48	38.15	Fri 23 Apr 10	Sat 15 Jan 11
	655	72.78	1	11.02	61.76	100.32	38.56	Mon 26 Apr 10	Fri 21 Jan 11
	660	73.33	1	11.14	62.2	101.17	38.98	Thu 29 Apr 10	Thu 27 Jan 11
	665	73.89	1	11.26	62.63	102.03	39.4	Sun 2 May 10	Wed 2 Feb 11
	670	74.44	1	11.38	63.07	102.89	39.82	Wed 5 May 10	Tue 8 Feb 11
	675	75	1	11.5	63.5	103.75	40.25	Sat 8 May 10	Mon 14 Feb 11
	680	75.56	1	11.62	63.93	104.61	40.68	Tue 11 May 10	Sun 20 Feb 11
	685	76.11	1	11.75	64.36	105.48	41.12	Fri 14 May 10	Sat 26 Feb 11
	690	76.67	1	11.87	64.79	106.35	41.56	Mon 17 May 10	Fri 4 Mar 11
	695	77.22	1	12	65.22	107.23	42.01	Thu 20 May 10	Thu 10 Mar 11
	700	77.78	1	12.13	65.65	108.1	42.46	Sun 23 May 10	Wed 16 Mar 11
	705	78.33	1	12.26	66.07	108.99	42.91	Wed 26 May 10	Tue 22 Mar 11
	710	78.89	1	12.39	66.5	109.87	43.37	Sat 29 May 10	Tue 29 Mar 11
	715	79.44	1	12.53	66.92	110.76	43.84	Tue 1 Jun 10	Mon 4 Apr 11
	720	80	1	12.66	67.34	111.65	44.31	Fri 4 Jun 10	Sun 10 Apr 11
	725	80.56	1	12.8	67.76	112.55	44.79	Mon 7 Jun 10	Sat 16 Apr 11
	730	81.11	1	12.93	68.18	113.44	45.27	Thu 10 Jun 10	Sat 23 Apr 11
	735	81.67	1	13.07	68.59	114.35	45.75	Sun 13 Jun 10	Fri 29 Apr 11
	740	82.22	1	13.21	69.01	115.25	46.25	Wed 16 Jun 10	Thu 5 May 11
	745	82.78	1	13.35	69.42	116.16	46.74	Sat 19 Jun 10	Thu 12 May 11
	750	83.33	1	13.5	69.84	117.08	47.24	Mon 21 Jun 10	Wed 18 May 11
	755	83.89	1	13.64	70.25	118	47.75	Thu 24 Jun 10	Wed 25 May 11
	760	84.44	1	13.79	70.65	118.92	48.26	Sun 27 Jun 10	Tue 31 May 11
	765	85	1	13.94	71.06	119.84	48.78	Wed 30 Jun 10	Mon 6 Jun 11
	770	85.56	1	14.09	71.47	120.77	49.31	Sat 3 Jul 10	Mon 13 Jun 11
	775	86.11	1	14.24	71.87	121.71	49.84	Tue 6 Jul 10	Mon 20 Jun 11
	780	86.67	1	14.39	72.27	122.65	50.37	Thu 8 Jul 10	Sun 26 Jun 11
	785	87.22	1	14.55	72.68	123.59	50.91	Sun 11 Jul 10	Sun 3 Jul 11
	790	87.78	1	14.7	73.08	124.53	51.46	Wed 14 Jul 10	Sat 9 Jul 11
	795	88.33	1	14.86	73.47	125.48	52.01	Sat 17 Jul 10	Sat 16 Jul 11
	800	88.89	1	15.02	73.87	126.44	52.57	Tue 20 Jul 10	Sat 23 Jul 11
	805	89.44	1	15.18	74.26	127.4	53.14	Thu 22 Jul 10	Fri 29 Jul 11
	810	90	1	15.34	74.66	128.36	53.71	Sun 25 Jul 10	Fri 5 Aug 11
	815	90.56	1	15.51	75.05	129.33	54.28	Wed 28 Jul 10	Fri 12 Aug 11
	820	91.11	1	15.68	75.44	130.3	54.87	Sat 31 Jul 10	Fri 19 Aug 11
	825	91.67	1	15.84	75.82	131.28	55.46	Mon 2 Aug 10	Thu 25 Aug 11
	830	92.22	1	16.01	76.21	132.26	56.05	Thu 5 Aug 10	Thu 1 Sep 11
	835	92.78	1	16.19	76.59	133.24	56.65	Sun 8 Aug 10	Thu 8 Sep 11
	840	93.33	1	16.36	76.97	134.23	57.26	Tue 10 Aug 10	Thu 15 Sep 11
	845	93.89	1	16.54	77.35	135.23	57.88	Fri 13 Aug 10	Thu 22 Sep 11
	850	94.44	1	16.71	77.73	136.23	58.5	Mon 16 Aug 10	Thu 29 Sep 11
	855	95	1	16.89	78.11	137.23	59.13	Wed 18 Aug 10	Thu 6 Oct 11
	860	95.56	1	17.07	78.48	138.24	59.76	Sat 21 Aug 10	Thu 13 Oct 11
	865	96.11	1	17.26	78.85	139.26	60.4	Tue 24 Aug 10	Thu 20 Oct 11
	870	96.67	1	17.44	79.22	140.28	61.05	Thu 26 Aug 10	Thu 27 Oct 11
	875	97.22	1	17.63	79.59	141.3	61.71	Sun 29 Aug 10	Fri 4 Nov 11
	880	97.78	1	17.82	79.96	142.33	62.37	Tue 31 Aug 10	Fri 11 Nov 11
	885	98.33	1	18.01	80.32	143.36	63.04	Fri 3 Sep 10	Fri 18 Nov 11
	890	98.89	1	18.21	80.68	144.4	63.72	Sun 5 Sep 10	Fri 25 Nov 11
	895	99.44	1	18.4	81.04	145.45	64.4	Wed 8 Sep 10	Sat 3 Dec 11
	900	100	1	18.6	81.4	146.5	65.09	Fri 10 Sep 10	Sat 10 Dec 11
	905	100.56	1	18.8	81.76	147.55	65.79	Mon 13 Sep 10	Sat 17 Dec 11
	910	101.11	1	19	82.11	148.61	66.5	Wed 15 Sep 10	Sun 25 Dec 11
	915	101.67	1	19.2	82.46	149.68	67.21	Sat 18 Sep 10	Sun 1 Jan 12
	920	102.22	1	19.41	82.81	150.75	67.94	Mon 20 Sep 10	Mon 9 Jan 12
	925	102.78	1	19.62	83.16	151.83	68.67	Thu 23 Sep 10	Mon 16 Jan 12
	930	103.33	1	19.83	83.5	152.91	69.4	Sat 25 Sep 10	Tue 24 Jan 12
	935	103.89	1	20.04	83.85	154	70.15	Mon 27 Sep 10	Wed 1 Feb 12
	940	104.44	1	20.26	84.19	155.09	70.9	Thu 30 Sep 10	Wed 8 Feb 12
	945	105	1	20.48	84.52	156.19	71.66	Sat 2 Oct 10	Thu 16 Feb 12
	950	105.56	1	20.7	84.86	157.29	72.43	Tue 5 Oct 10	Fri 24 Feb 12
	955	106.11	1	20.92	85.19	158.41	73.21	Thu 7 Oct 10	Fri 2 Mar 12
	960	106.67	1	21.14	85.52	159.52	74	Sat 9 Oct 10	Sat 10 Mar 12
	965	107.22	1	21.37	85.85	160.65	74.79	Tue 12 Oct 10	Sun 18 Mar 12
	970	107.78	1	21.6	86.18	161.78	75.6	Thu 14 Oct 10	Mon 26 Mar 12
	975	108.33	1	21.83	86.5	162.91	76.41	Sat 16 Oct 10	Tue 3 Apr 12
	980	108.89	1	22.07	86.82	164.05	77.23	Mon 18 Oct 10	Wed 11 Apr 12
	985	109.44	1	22.3	87.14	165.2	78.06	Thu 21 Oct 10	Thu 19 Apr 12
	990	110	1	22.54	87.46	166.36	78.9	Sat 23 Oct 10	Fri 27 Apr 12
	995	110.56	1	22.78	87.77	167.52	79.74	Mon 25 Oct 10	Sat 5 May 12
	1000	111.11	1	23.03	88.08	168.68	80.6	Wed 27 Oct 10	Sun 13 May 12

## Sheet2
A basic power formula for calculating a range of dates for completion User Stories
		Main Title

Points_per_Iteration	27.0000
Weeks_per_Iteration	3.0000
Base_Multiplier	0.0040
Power	1.9000

Max_Date_Multiplier	2.0000
Min_Date_Multiplier	0.8000

Story_Points	500.0000
Date_Today	Wed 18 Feb 09

Weeks_Remaining_Base_Reference	55.5556

Delta_Correction	8.2612

Min_Weeks_to_Completion	48.9466
Max_Weeks_to_Completion	72.0779

Min_Completion_Date	Tue 26 Jan 10
Max_Completion_Date	Wed 7 Jul 10

	Story Points	Weeks_Remaining	DC	MinWeeks	MaxWeeks	Range

	1	0.11	0	0.11	0.11	0
	5	0.56	0	0.55	0.56	0
	10	1.11	0	1.11	1.12	0.01
	15	1.67	0.01	1.66	1.69	0.03
	20	2.22	0.02	2.21	2.26	0.05
	25	2.78	0.03	2.76	2.83	0.08
	30	3.33	0.04	3.3	3.41	0.11
	35	3.89	0.05	3.85	3.99	0.15
	40	4.44	0.07	4.39	4.58	0.19
	45	5	0.09	4.93	5.17	0.24
	50	5.56	0.1	5.47	5.76	0.29
	55	6.11	0.12	6.01	6.36	0.35
	60	6.67	0.15	6.55	6.96	0.41
	65	7.22	0.17	7.09	7.56	0.48
	70	7.78	0.2	7.62	8.17	0.55
	75	8.33	0.22	8.15	8.78	0.63
	80	8.89	0.25	8.69	9.4	0.71
	85	9.44	0.29	9.22	10.01	0.8
	90	10	0.32	9.75	10.64	0.89
	95	10.56	0.35	10.27	11.26	0.99
	100	11.11	0.39	10.8	11.89	1.09
	105	11.67	0.43	11.33	12.52	1.19
	110	12.22	0.47	11.85	13.15	1.3
	115	12.78	0.51	12.37	13.79	1.42
	120	13.33	0.55	12.89	14.43	1.54
	125	13.89	0.59	13.41	15.08	1.66
	130	14.44	0.64	13.93	15.72	1.79
	135	15	0.69	14.45	16.37	1.92
	140	15.56	0.74	14.97	17.03	2.06
	145	16.11	0.79	15.48	17.68	2.2
	150	16.67	0.84	16	18.34	2.35
	155	17.22	0.89	16.51	19.01	2.5
	160	17.78	0.95	17.02	19.67	2.65
	165	18.33	1.01	17.53	20.34	2.81
	170	18.89	1.06	18.04	21.02	2.98
	175	19.44	1.12	18.55	21.69	3.15
	180	20	1.19	19.05	22.37	3.32
	185	20.56	1.25	19.56	23.05	3.5
	190	21.11	1.31	20.06	23.74	3.68
	195	21.67	1.38	20.56	24.43	3.87
	200	22.22	1.45	21.06	25.12	4.06
	205	22.78	1.52	21.56	25.81	4.25
	210	23.33	1.59	22.06	26.51	4.45
	215	23.89	1.66	22.56	27.21	4.65
	220	24.44	1.74	23.06	27.92	4.86
	225	25	1.81	23.55	28.62	5.07
	230	25.56	1.89	24.04	29.33	5.29
	235	26.11	1.97	24.54	30.05	5.51
	240	26.67	2.05	25.03	30.76	5.74
	245	27.22	2.13	25.52	31.48	5.96
	250	27.78	2.21	26.01	32.2	6.2
	255	28.33	2.3	26.49	32.93	6.44
	260	28.89	2.38	26.98	33.66	6.68
	265	29.44	2.47	27.47	34.39	6.92
	270	30	2.56	27.95	35.12	7.17
	275	30.56	2.65	28.43	35.86	7.43
	280	31.11	2.75	28.91	36.6	7.69
	285	31.67	2.84	29.4	37.35	7.95
	290	32.22	2.93	29.87	38.09	8.22
	295	32.78	3.03	30.35	38.84	8.49
	300	33.33	3.13	30.83	39.59	8.76
	305	33.89	3.23	31.31	40.35	9.04
	310	34.44	3.33	31.78	41.11	9.33
	315	35	3.43	32.25	41.87	9.61
	320	35.56	3.54	32.72	42.63	9.91
	325	36.11	3.64	33.2	43.4	10.2
	330	36.67	3.75	33.67	44.17	10.5
	335	37.22	3.86	34.13	44.94	10.81
	340	37.78	3.97	34.6	45.72	11.12
	345	38.33	4.08	35.07	46.5	11.43
	350	38.89	4.19	35.53	47.28	11.75
	355	39.44	4.31	36	48.06	12.07
	360	40	4.43	36.46	48.85	12.39
	365	40.56	4.54	36.92	49.64	12.72
	370	41.11	4.66	37.38	50.44	13.05
	375	41.67	4.78	37.84	51.23	13.39
	380	42.22	4.9	38.3	52.03	13.73
	385	42.78	5.03	38.76	52.83	14.08
	390	43.33	5.15	39.21	53.64	14.43
	395	43.89	5.28	39.67	54.45	14.78
	400	44.44	5.41	40.12	55.26	15.14
	405	45	5.54	40.57	56.07	15.5
	410	45.56	5.67	41.02	56.89	15.87
	415	46.11	5.8	41.47	57.71	16.23
	420	46.67	5.93	41.92	58.53	16.61
	425	47.22	6.07	42.37	59.36	16.99
	430	47.78	6.2	42.82	60.18	17.37
	435	48.33	6.34	43.26	61.01	17.75
	440	48.89	6.48	43.71	61.85	18.14
	445	49.44	6.62	44.15	62.69	18.54
	450	50	6.76	44.59	63.52	18.93
	455	50.56	6.91	45.03	64.37	19.34
	460	51.11	7.05	45.47	65.21	19.74
	465	51.67	7.2	45.91	66.06	20.15
	470	52.22	7.34	46.35	66.91	20.57
	475	52.78	7.49	46.78	67.77	20.98
	480	53.33	7.64	47.22	68.62	21.41
	485	53.89	7.8	47.65	69.48	21.83
	490	54.44	7.95	48.08	70.34	22.26
	495	55	8.1	48.52	71.21	22.69
	500	55.56	8.26	48.95	72.08	23.13
	505	56.11	8.42	49.38	72.95	23.57
	510	56.67	8.58	49.8	73.82	24.02
	515	57.22	8.74	50.23	74.7	24.47
	520	57.78	8.9	50.66	75.58	24.92
	525	58.33	9.06	51.08	76.46	25.38
	530	58.89	9.23	51.51	77.35	25.84
	535	59.44	9.39	51.93	78.23	26.3
	540	60	9.56	52.35	79.12	26.77
	545	60.56	9.73	52.77	80.02	27.25
	550	61.11	9.9	53.19	80.91	27.72
	555	61.67	10.07	53.61	81.81	28.2
	560	62.22	10.25	54.03	82.71	28.69
	565	62.78	10.42	54.44	83.62	29.18
	570	63.33	10.6	54.86	84.53	29.67
	575	63.89	10.77	55.27	85.44	30.17
	580	64.44	10.95	55.68	86.35	30.67
	585	65	11.13	56.09	87.27	31.17
	590	65.56	11.31	56.5	88.18	31.68
	595	66.11	11.5	56.91	89.1	32.19
	600	66.67	11.68	57.32	90.03	32.71
	605	67.22	11.87	57.73	90.96	33.23
	610	67.78	12.05	58.13	91.89	33.75
	615	68.33	12.24	58.54	92.82	34.28
	620	68.89	12.43	58.94	93.75	34.81
	625	69.44	12.62	59.35	94.69	35.35
	630	70	12.82	59.75	95.63	35.88
	635	70.56	13.01	60.15	96.58	36.43
	640	71.11	13.21	60.55	97.52	36.97
	645	71.67	13.4	60.95	98.47	37.53
	650	72.22	13.6	61.34	99.42	38.08
	655	72.78	13.8	61.74	100.38	38.64
	660	73.33	14	62.13	101.33	39.2
	665	73.89	14.2	62.53	102.29	39.77
	670	74.44	14.41	62.92	103.26	40.34
	675	75	14.61	63.31	104.22	40.91
	680	75.56	14.82	63.7	105.19	41.49
	685	76.11	15.02	64.09	106.16	42.07
	690	76.67	15.23	64.48	107.13	42.66
	695	77.22	15.44	64.87	108.11	43.24
	700	77.78	15.66	65.25	109.09	43.84
	705	78.33	15.87	65.64	110.07	44.43
	710	78.89	16.08	66.02	111.06	45.03
	715	79.44	16.3	66.4	112.04	45.64
	720	80	16.52	66.79	113.03	46.25
	725	80.56	16.74	67.17	114.03	46.86
	730	81.11	16.96	67.55	115.02	47.48
	735	81.67	17.18	67.93	116.02	48.1
	740	82.22	17.4	68.3	117.02	48.72
	745	82.78	17.62	68.68	118.03	49.35
	750	83.33	17.85	69.05	119.03	49.98
	755	83.89	18.08	69.43	120.04	50.61
	760	84.44	18.3	69.8	121.05	51.25
	765	85	18.53	70.17	122.07	51.89
	770	85.56	18.76	70.54	123.08	52.54
	775	86.11	19	70.91	124.1	53.19
	780	86.67	19.23	71.28	125.13	53.84
	785	87.22	19.46	71.65	126.15	54.5
	790	87.78	19.7	72.02	127.18	55.16
	795	88.33	19.94	72.38	128.21	55.83
	800	88.89	20.18	72.75	129.24	56.5
	805	89.44	20.42	73.11	130.28	57.17
	810	90	20.66	73.47	131.32	57.85
	815	90.56	20.9	73.83	132.36	58.53
	820	91.11	21.15	74.19	133.4	59.21
	825	91.67	21.39	74.55	134.45	59.9
	830	92.22	21.64	74.91	135.5	60.59
	835	92.78	21.89	75.27	136.55	61.29
	840	93.33	22.14	75.62	137.61	61.99
	845	93.89	22.39	75.98	138.67	62.69
	850	94.44	22.64	76.33	139.73	63.39
	855	95	22.89	76.68	140.79	64.11
	860	95.56	23.15	77.04	141.86	64.82
	865	96.11	23.41	77.39	142.92	65.54
	870	96.67	23.66	77.74	143.99	66.26
	875	97.22	23.92	78.08	145.07	66.98
	880	97.78	24.18	78.43	146.14	67.71
	885	98.33	24.45	78.78	147.22	68.45
	890	98.89	24.71	79.12	148.31	69.18
	895	99.44	24.97	79.47	149.39	69.92
	900	100	25.24	79.81	150.48	70.67
	905	100.56	25.51	80.15	151.57	71.42
	910	101.11	25.77	80.49	152.66	72.17
	915	101.67	26.04	80.83	153.75	72.92
	920	102.22	26.31	81.17	154.85	73.68
	925	102.78	26.59	81.51	155.95	74.44
	930	103.33	26.86	81.84	157.05	75.21
	935	103.89	27.14	82.18	158.16	75.98
	940	104.44	27.41	82.51	159.27	76.75
	945	105	27.69	82.85	160.38	77.53
	950	105.56	27.97	83.18	161.49	78.31
	955	106.11	28.25	83.51	162.61	79.1
	960	106.67	28.53	83.84	163.73	79.89
	965	107.22	28.81	84.17	164.85	80.68
	970	107.78	29.1	84.5	165.97	81.47
	975	108.33	29.38	84.83	167.1	82.27
	980	108.89	29.67	85.15	168.23	83.08
	985	109.44	29.96	85.48	169.36	83.89
	990	110	30.25	85.8	170.5	84.7
	995	110.56	30.54	86.12	171.63	85.51
	1000	111.11	30.83	86.45	172.77	86.33

## Sheet3
Comparison of two Algorithms